# NASA Space Apps Backend – Implementation Plan for Build Agent

Oct 10, 2026 · @Yusuf

## 1. Mission and working rules

Build the NASA Space Apps backend (ASP.NET Core + SQL Server) exactly as specified in the design doc, in 7 ordered phases, with tests, so the React and Flutter teams can integrate against a stable contract.

Sources of truth, in priority order

- The Backend Design & API Contract: structure, data-model changes, auth, conventions, every endpoint. Section numbers below (for example "design 7.3") point into it.

- The PRD (NASA_Space_Apps_Platform_PRD.docx): the reason behind each requirement.

- The ERD script (ERD_Script.sql): the starting schema. Where it differs from design section 4, section 4 wins.

If two sources conflict, follow the higher one and record the conflict in docs/DECISIONS.md.

Working rules

- Work phase by phase. Do not start a phase until the previous phase's acceptance checks pass.

- The contract is fixed. Paths, field names, status codes and error codes match design sections 6 and 7 exactly. A needed deviation goes into docs/DECISIONS.md with the reason; never change it silently.

- Never invent requirements. Where the PRD is open, use the default in design section 9 and note it.

- Every endpoint ships with a FluentValidation validator, an authorization policy from design section 5, and tests: happy path, 401, 403, and one validation failure.

- Business rules live in Application, never in controllers. Only Infrastructure references EF Core, SignalR or JWT libraries.

- No secrets in the repository. Connection string, JWT key and seed admin password come from environment variables. Passwords, tokens and Authorization headers never reach logs or responses (except the one-time reveals in design 7.2 and 7.10).

- One branch per phase, small commits per task, message format phase-N: task.

- Keep docs/PROGRESS.md current: tick each task as it passes its check. If blocked, write the blocker there, finish what is independent, and report.

- Finish with a runnable system: dotnet build, dotnet test and the app start with a documented command.

## 2. Fixed technical decisions

These are settled. The agent applies them without asking and without proposing alternatives.

| Area | Decision |
| --- | --- |
| Projects | NasaSpaceApps.Api, .Application, .Domain, .Infrastructure, plus tests/NasaSpaceApps.Application.Tests and tests/NasaSpaceApps.Api.Tests (design 3). Nullable reference types on. |
| Database | SQL Server 2022, EF Core code-first with migrations. Tables singular PascalCase as in the ERD. Integer identity keys. Enums stored as strings with check constraints. All times datetime2 in UTC through an IClock. |
| Schema | ERD script plus every change and new table in design 4. The first migration contains all of it. |
| Packages | Microsoft.EntityFrameworkCore.SqlServer, Microsoft.AspNetCore.Authentication.JwtBearer, FluentValidation with its DI extensions, Serilog.AspNetCore, ASP.NET Core OpenAPI with Swagger UI, xunit, Testcontainers.MsSql. Anything else needs a line in docs/DECISIONS.md. |
| Routing | Controllers with the literal prefix api/v1 (no versioning library). Hubs at /hubs/standings and /hubs/operations. |
| JSON | System.Text.Json, camelCase, enums as strings, ISO 8601 UTC. |
| Results and errors | Services return Result<T> with an AppError(code, httpStatus, message). One base controller maps it to RFC 7807 application/problem+json with the code values in design 6. |
| Tokens | JWT access token 30 minutes. Refresh token 7 days, random 32 bytes, stored as SHA-256 hash, rotated on every use. |
| Passwords | PasswordHasher (PBKDF2). Lockout after 5 failures for 5 minutes. |
| Idempotency | Idempotency-Key on POST /requests and POST /game/answers, stored for 24 hours per caller. |
| Caching | IMemoryCache: standings by version, sponsors and public content 60 seconds to 5 minutes. |
| Local run | docker-compose.yml with SQL Server, README.md with the three commands to migrate, seed and run. |

The agent writes down anything it had to choose that this table does not cover. One line in docs/DECISIONS.md is enough.

## 3. Phases 0 and 1: foundation, database, auth, teams

### Phase 0. Scaffold and shared plumbing

Goal: an empty but production-shaped API that builds, starts, logs safely and returns errors in the agreed format.

- ☐ Create the solution, the four src projects and two test projects. Reference direction: Api → Application → Domain, Infrastructure → Application (design 3).

- ☐ Add Common in Application: Result<T>, AppError, Paged<T>, ICurrentUser, IClock, INotifier (a no-op implementation for now).

- ☐ Add a base API controller that maps Result<T> to HTTP, and a global handler that returns application/problem+json with code, errors and traceId (design 6).

- ☐ Add correlation-id middleware (X-Correlation-Id in and out) and Serilog JSON logging with a masking policy for password, accessToken, refreshToken, Authorization.

- ☐ Add GET /health/live and GET /health/ready (database check), OpenAPI with Swagger UI, CORS from configuration, and rate-limiter policies named login, write and public.

- ☐ Bind configuration through validated options classes. The app fails at startup, naming the missing key, if the connection string or JWT key is absent.

- ☐ Add docker-compose.yml, a README.md with migrate, seed and run commands, docs/DECISIONS.md and docs/PROGRESS.md.

Acceptance checks:

- dotnet build and dotnet test pass with zero warnings treated as errors.

- GET /health/live returns 200; /health/ready returns 200 with the database up and 503 with it down.

- A deliberately thrown exception returns 500 with code: server_error and a traceId only, with no stack trace.

- A log line produced while logging an object containing password shows the value masked.

### Phase 1. Database, authentication, teams and challenges

Goal: every table exists with its integrity rules, and a team or staff member can sign in and read the core data (design 4, 5, 7.1, 7.2).

- ☐ Write Domain entities and enums for every table in design 4, existing and new, including AppUser, RefreshToken, PrizeGame, EventSetting, AuditLog, CoreTeamMember, MediaItem.

- ☐ Write EF Core configurations: keys, foreign keys, every unique and filtered unique index, check constraints (statuses, Score >= 0, ISJSON, RefreshToken owner is exactly one of team or user), RowVersion on JudgeScore, and the extra indexes in design 8.

- ☐ Create one migration named Initial. Add a SaveChanges interceptor for CreatedAt, UpdatedAt, UpdatedBy and AuditLog writes.

- ☐ Seed on first run: the Admin account from environment variables, and sponsor tier Tier 1 with priority 1 and bannerEnabled true. Add a Development-only seeder with 3 challenges, 5 teams with 3 students each, 2 judges, 1 organizer, 1 mentor and 3 criteria.

- ☐ Auth: POST /auth/login, /auth/staff/login, /auth/refresh, /auth/logout, GET /auth/me; JWT issuing; refresh rotation; lockout; the five policies from design 5.

- ☐ Teams: GET /teams with search and paging, /teams/me, /teams/{id}, /students, /challenge, GET and PUT /teams/{id}/project; Admin POST and PUT /teams, reset-password, import, student create, update, delete. Enforce the "Team (own)" rule in one reusable authorization handler.

- ☐ Challenges: list, get, and Admin create, update, delete. The /questions sub-route waits for phases 3 and 5.

Acceptance checks (each is an automated test):

- The migration applies to an empty SQL Server and the database itself rejects: a student with no team, a second team with the same username, a second project for one team, a duplicate (TeamId, JudgeId, CriterionId) score.

- Team login returns role: Team and teamId. A wrong password and an unknown username return the same 401 auth.invalid_credentials. The 6th attempt within the window returns auth.account_locked.

- Reusing a refresh token that was already rotated returns 401.

- A Team token calling GET /teams/{otherTeamId} gets 403; calling GET /teams gets 403; a Judge calling GET /teams?search=<username> gets 200.

- Searching by a numeric team id returns that team first.

- POST /teams/import returns one-time credentials; no response anywhere contains passwordHash or a stored password.

## 4. Phases 2 and 3: operations, judging, standings

### Phase 2. Service requests and attendance

Goal: a team can ask for help and an organizer can work the queue and take attendance (design 7.3, 7.4).

- ☐ Add an IdempotencyRecord table (key, caller, status code, response body, created at) in a second migration, AddIdempotency, and an action filter that replays the stored response for 24 hours. This table is not in the design; note it in docs/DECISIONS.md.

- ☐ Add an ISettings service that reads EventSetting through a cache. Phase 2 needs EventDays and EventTimeZone; the Admin endpoints for settings come in phase 5.

- ☐ Implement the request workflow as a pure domain method with a transition table (design 7.3). Map the filtered-unique-index violation to 409 request.duplicate_open and return the existing requestId.

- ☐ Implement POST /requests, GET /requests/mine, GET /requests/{id}, POST /requests/{id}/cancel, GET and PATCH /organizer/requests. Mentor access is limited to Mentor type in the query and in the update.

- ☐ Call INotifier.RequestCreated and RequestUpdated after each commit. The implementation is still a no-op.

- ☐ Implement GET /attendance/team/{teamId}, POST /attendance (bulk upsert, one transaction), GET /attendance/summary, GET /attendance/export.

Acceptance checks:

- A Team creates a Mentor request and gets 201. A second open Mentor request gets 409 request.duplicate_open; an open Organizer request alongside it is allowed.

- Two calls with the same Idempotency-Key return identical bodies and leave one row.

- A transition test covers every pair of statuses. Only the four allowed moves in design 7.3 pass; all others return 409 request.invalid_transition.

- A Mentor listing requests sees only Mentor type, and a Mentor PATCH on an Organizer request returns 403.

- A Team cannot cancel an InProgress request (409) or read another team's request (403).

- Attendance: a studentId from another team returns 400; a date outside EventDays returns 400; posting twice for the same student and day leaves one row with the newer markedBy and timestamp; the summary counts unmarked students.

### Phase 3. Judging and standings

Goal: judges submit valid scores and the public board computes correctly, still over REST only (design 7.5, 7.6, 8).

- ☐ Criteria: GET /judging/criteria, and Admin create, update, delete. maxScore is locked and delete is refused once any score uses the criterion.

- ☐ GET /judging/teams/{teamId} (the judge workspace in one call), GET /challenges/{id}/questions?type=Evaluation, GET /judging/challenges/{id}/suggested-questions. Do not build the generate endpoint; it waits for the provider decision (design 9, item 12).

- ☐ POST /judging/scores: validate every rule in design 7.5, upsert all rows in one transaction, handle rowVersion, take the judge from the token, and increment the standings version in the same transaction.

- ☐ GET /judging/scores/mine and GET /judging/scores, honouring JudgesSeeOthers.

- ☐ StandingsService: the formula in design 8, competition ranking, isTied, unscored teams last with rank: null, in-memory cache keyed by version. Endpoints GET /standings, GET /standings/teams/{id}, PUT /standings/tie-breaks, GET /standings/export.

- ☐ Call INotifier.StandingsChanged after the score transaction commits.

Acceptance checks:

- Formula unit test. Criteria A (max 10, weight 60) and B (max 10, weight 40). Team X: A scored 8 and 6 by two judges, B scored 9 and 9. Team Y: A 10, B 5, one judge. X totals 78.0 and Y totals 80.0, so Y ranks first. Two teams both at 78.0 get ranks 1, 1, 3 and isTied: true.

- A score of 10.01 against a maximum of 10 returns 400, and none of the submission's other rows are saved. A submission missing a criterion returns 400. A judgeId in the body is ignored.

- A Judge reading all scores with JudgesSeeOthers=false gets 403; an Organizer gets 200.

- A stale rowVersion returns 409 score.stale. Resubmitting leaves the row count unchanged and raises version by one.

- GET /standings with no token returns 200 and contains no judge names, comments or criterion breakdown while ShowCriterionBreakdown is false.

- Two judges posting scores for the same team at the same time are both saved, and the final board matches a manual calculation.

- PUT /standings/tie-breaks rejects team ids that are not actually tied (400) and is written to AuditLog.

## 5. Phases 4 to 6: real time, engagement, hardening

### Phase 4. Real time

Goal: the standings board and the organizer queue update without a refresh (design 8).

- ☐ Implement SignalRNotifier behind INotifier. Notifier failures are logged and never fail the REST call that triggered them.

- ☐ StandingsHub at /hubs/standings, anonymous. Pushes the GET /standings body as standingsUpdated, debounced to one push per 500 ms with the latest version always sent last.

- ☐ OperationsHub at /hubs/operations, token required, with the access_token query-string fallback for WebSockets. On connect the server adds the caller to organizers, mentors or team-{teamId} by role; clients cannot join groups.

- ☐ Send requestCreated and requestUpdated to the groups defined in design 8.

- ☐ Add docs/realtime.md with connection examples for React (@microsoft/signalr) and Flutter (signalr_netcore), including reconnect-then-refetch.

Acceptance checks (integration tests with a SignalR client):

- A judge posts scores and an anonymous StandingsHub client receives standingsUpdated within 2 seconds with a higher version.

- Ten score writes within 300 ms produce at most 2 pushes, and the last push holds the newest version.

- Team A's connection never receives events about Team B. An Organizer receives requestCreated; a Mentor receives it only for Mentor type.

- Connecting to OperationsHub without a token is rejected.

- Stopping the SignalR layer in a test does not make POST /judging/scores fail.

### Phase 5. Game, sponsors, public content, admin

Goal: all remaining endpoints in design 7.7 to 7.10.

- ☐ Game: GET /game/questions, POST /game/answers, GET /game/answers/mine, GET /game/leaderboard, admin question CRUD with publish and unpublish, prize games, POST .../winner. Winner rules are strategy classes chosen by PrizeGame.WinnerRule. Add the type=Game branch to GET /challenges/{id}/questions.

- ☐ Sponsors: public list, banner, tiers, admin CRUD, logo upload through an IFileStorage interface with a local-disk implementation served as static files. Accept PNG, JPEG, WebP, SVG up to 2 MB, checking the file signature, not only the extension.

- ☐ Public content: overview, core team, media, admin CRUD, media upload (up to 10 MB). Add the cache headers from design 7.8 and 7.9.

- ☐ Admin: users (creating a Judge also creates the Judge row), password reset, GET and PUT /admin/settings with per-key validation, GET /admin/audit-logs.

- ☐ Refuse login and refresh for inactive users and Inactive teams.

Acceptance checks:

- No Team-facing response contains the text of any correctAnswer. A test serializes every game response and searches for it.

- A second answer returns 409 game.already_answered. An answer before opensAt, after closesAt or on an unpublished question returns 409 game.closed. Text answers match case-insensitively after trimming.

- Winner rule test with 3 teams: A and B both 20 points, B finished earlier, C 10 points. MostPointsThenEarliest ranks B, A, C. Two teams identical on points and time are both marked tied, and POST .../winner with a team that is not at the top returns 400.

- Banner returns only active sponsors in tiers with bannerEnabled, ordered by tier priority then displayOrder. An executable renamed to .png is rejected with 400; a 3 MB image is rejected with 400.

- PUT /admin/settings/Unknown returns 400; an invalid date in EventDays returns 400; every accepted change appears in AuditLog.

- A deactivated staff user cannot sign in or refresh.

### Phase 6. Hardening and handover

Goal: the system is safe to run on event day and another developer can pick it up.

- ☐ Generate a role-matrix test from design 5: for every endpoint and every role, assert the expected status (2xx, 401 or 403).

- ☐ Commit docs/openapi.json exported from the running app, and a requests.http file with one working call per endpoint.

- ☐ Add HTTPS redirect, HSTS, security headers, and confirm the rate limiter on login, answer and request creation.

- ☐ Check query plans for team search, the request queue, attendance by team and day, and standings. Add an index only where a plan shows a scan, and record it.

- ☐ Run a smoke load test. Default size: 100 teams, 20 judges, 50 standings viewers, 5 minutes. Replace with the real expected numbers when the organizers give them.

- ☐ Write docs/runbook.md: idempotent migration script, database backup and restore steps, health checks, event-day checklist, how to reset a team password.

- ☐ Write docs/HANDOVER.md: every deviation from the design, every default still in force from design section 9, and anything not built.

Acceptance checks:

- The role-matrix test passes and covers 100% of endpoints in design section 7.

- Every route in the running app appears in docs/openapi.json and in design section 7, and the reverse, except the three health and hub routes.

- A restore of a fresh backup into an empty database succeeds and /health/ready returns 200.

- The smoke test finishes with no 5xx and with GET /standings answering in under 500 ms at the 95th percentile on the test machine.

## 6. Definition of done and reporting

The backend is done when every acceptance check in sections 3 to 5 passes from a clean clone using only the commands in README.md.

| Test layer | Tool | Covers |
| --- | --- | --- |
| Unit | xUnit | Standings formula and ranking, request transitions, winner rules, validators, score range rules |
| Integration | xUnit and Testcontainers (real SQL Server) | Migrations, database constraints, every endpoint with its role, idempotency, concurrency |
| Real time | xUnit with the SignalR .NET client | Hub groups, debounce, push content |
| Contract | Generated openapi.json compared with design section 7 | No missing and no extra endpoints |

The performance numbers in phase 6 are starting targets. The organizers' real team and judge counts replace them when known.

Also required for done

- No TODO in src unless it is listed in docs/PROGRESS.md.

- No secrets in the repository or its history. Logs from a full test run contain no password or token.

- docs/DECISIONS.md and docs/HANDOVER.md are complete.

Report at the end of every phase (a short message, not a file): what was built, how many acceptance checks passed out of how many, deviations from the design with reasons, blockers.

Stop and ask the user, do not guess, when

- The design and the PRD contradict each other in a way that changes the data model or an endpoint's behaviour.

- A step needs a paid service, a credential or a hosting decision (design 9, item 10).

- A default from design section 9 turns out to make an acceptance check impossible.

For open decisions 1 (criteria), 3 (tie-breaks), 6 (game winner rule) and 10 (hosting), the agent builds to the default, keeps it switchable, and lists it in the handover so a person can confirm it.

## 7. Prompt for the build agent

Give the agent this prompt, this doc, the design doc, and the two original files (PRD and ERD script). Without the design doc it cannot work.

You are building the backend for the NASA Space Apps hackathon platform: an ASP.NET Core REST + SignalR API over SQL Server, used by a React web app and a Flutter team app.

Read these first, in full, before writing code:
1. Backend Design & API Contract (design doc): https://claude.ai/code/artifact/db537686-c978-48e4-a4cf-ed781532d407
2. This implementation plan: https://claude.ai/code/artifact/d90899bb-2e7c-4ca9-8087-178eb1d8154b
3. NASA_Space_Apps_Platform_PRD.docx and ERD_Script.sql (attached)

Rules:
- Follow the plan's phases 0 to 6 in order. Do not start a phase until the previous phase's acceptance checks pass.
- The design doc is the contract. Paths, fields, status codes and error codes must match it exactly. Record any deviation, with the reason, in docs/DECISIONS.md.
- Where the ERD and the design doc differ, the design doc wins (its section 4).
- Use the technical decisions in plan section 2 without asking. Do not add packages beyond that list without noting it in docs/DECISIONS.md.
- Never invent requirements. For open decisions use the defaults in design section 9 and keep them switchable.
- Every endpoint gets a validator, an authorization policy, and tests (success, 401, 403, one validation failure).
- No secrets in the repo, and no passwords or tokens in logs or responses.
- Keep docs/PROGRESS.md updated by ticking tasks as their checks pass.
- After each phase, send me a short report: what was built, acceptance checks passed out of total, deviations, blockers.
- Stop and ask me if the design and PRD contradict each other in a way that changes data or behaviour, or if a step needs a credential, a paid service or a hosting decision.

Start with Phase 0. Create the solution and the plumbing, run the Phase 0 acceptance checks, then report.